## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
s1 | s1 | US-001 | CV introduction: Principles Of Image Processing, Object Detection, CNNs Overview | MUST HAVE | None | Ruby Kushwah | Completed
s1 | s1 | US-002 | OCR introduction: Introduction To Text Extraction, Text Recognizer | MUST HAVE | None | Ruby Kushwah | Completed
s2 | s2 | US-003 | ANPR Implementation: Reading & Processing Of Pre-Trained Images & Video To Detect Number Plates | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s2 | s2 | US-004 | YOLO Models Training: Training Various YOLO Models for Number Plate Detection | COULD HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s2 | s2 | US-005 | Image Processing: Training Images in Various Formats (Grayscale, Normal, Blurred) & Extracting Text | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s2 | s2 | US-006 | Video Processing: Capturing & Annotating Frames to Detect Vehicles (Cars, Buses, Trucks, etc.) | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-007 | Building the ATCC System: Training and testing vehicle classification models | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-008 | Training and Testing Vehicle Classification Models (Cars, Motorcycles, Trucks, etc.) | SHOULD HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-009 | Deep Learning-Based Vehicle Classification Model Development | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-010 | Creating A Live Object Tracker: Track Vehicles Using System Camera Or Web Cam | COULD HAVE | Working System Camera/Webcam, Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-011 | Data Processing: Sorting Vehicles, Number Plates, and Frame IDs in a CSV File | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s3 | s3 | US-012 | Visualization: Displaying Number Plates & Vehicles in the Traffic Video | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s4 | s4 | US-013 | Helmet Detection Implementation: Identifying bikers without helmets | MUST HAVE | Python Libraries [OpenCV, YOLO] | Ruby Kushwah | Completed
s4 | s4 | US-014 | Triple Riding Detection: Identifying motorcycles carrying more than two passengers | MUST HAVE | Python Libraries [OpenCV, YOLO] | Ruby Kushwah | Completed
s4 | s4 | US-015 | Front-end Development: Designing and implementing the UI for system interaction | MUST HAVE | React/HTML/CSS/JavaScript | Ruby Kushwah | Completed
s4 | s4 | US-016 | Back-end Integration using Flask: Connecting front-end with ANPR & ATCC system | MUST HAVE | Flask, Python | Ruby Kushwah | Completed
s4 | s4 | US-017 | System Integration: Combining ANPR and ATCC into a real-time platform | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s4 | s4 | US-018 | Real-Time Optimization: Improving model inference speed and accuracy | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed
s4 | s4 | US-019 | Vehicle Classification into Different Categories (Cars, Buses, Motorcycles, Trucks) | MUST HAVE | Python Libraries [OpenCV, OCR, EasyOCR, Tesseract, Ultralytics, etc.] & YOLO Models | Ruby Kushwah | Completed

## Sheet2
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 138 | 12 | 12 | 11 | 17 | 15 | 6 | 0 | 12 | 14 | 10 | 14 | 14 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Principles Of Image Processing, Object Detection | 2025-02-07 | 2025-02-07 | Ruby Kushwah | Others | 3- Completed | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-001 | TID-02 | CNNs Overview | 2025-02-10 | 2025-02-10 | Ruby Kushwah | Others | 3- Completed | 4 | Day 4: 2; Day 5: 2
US-002 | TID-01 | Intoduction to Text Extraction | 2025-02-11 | 2025-02-11 | Ruby Kushwah | Others | 3- Completed | 6 | Day 8: 3; Day 9: 2; Day 10: 1
US-002 | TID-02 | Intoduction To text Recognization | 2025-02-12 | 2025-02-12 | Ruby Kushwah | Others | 3- Completed | 4 | Day 11: 3; Day 12: 1
SPRINT 2
US-003 | TID-01 | Reading & Processing Of The Pre-Trained Images | 2025-02-13 | 2025-02-13 | Ruby kushwah | Build | 3- Completed | 4 | Day 1: 4
US-003 | TID-02 | Reading & Processing Of The Pre-Trained Video | 2025-02-14 | 2025-02-14 | Ruby kushwah | Build | 3- Completed | 5 | Day 2: 5
US-003 | TID-03 | Extracting Text From Them To Detect Number Plates | 2025-02-17 | 2025-02-17 | Ruby kushwah | Build | 3- Completed | 4 | Day 3: 4
US-004 | TID-01 | Training Of Various Yolo Models For Detecting The Number Plates | 2025-02-18 | 2025-02-18 | Ruby kushwah | Coding | 3- Completed | 5 | Day 4: 5
US-005 | TID-01 | Training Of Images In Gray Scale Format | 2025-02-19 | 2025-02-19 | Ruby kushwah | Coding | 3- Completed | 5 | Day 5: 5
US-005 | TID-02 | Training Of Images In Normal Format | 2025-02-20 | 2025-02-20 | Ruby kushwah | Coding | 3- Completed | 3 | Day 8: 3
US-005 | TID-03 | Training Of Images In Blurred Format | 2025-02-21 | 2025-02-21 | Ruby kushwah | Coding | 3- Completed | 4 | Day 9: 4
US-005 | TID-04 | Extracting Text From The Trained Image | 2025-02-24 | 2025-02-24 | Ruby kushwah | Coding | 3- Completed | 4 | Day 10: 4
US-006 | TID-01 | Reading & Capturing Of The Frames In The Video | 2025-02-25 | 2025-02-25 | Ruby kushwah | Coding | 3- Completed | 5 | Day 11: 5
US-006 | TID-02 | Annotate It To Detect The Vechicles In It By Different Formats Like Cars, Buses, Trucks, etc.. | 2025-02-26 | 2025-02-26 | Ruby kushwah | Design | 3- Completed | 6 | Day 12: 6
SPRINT 3 BACKLOG
US-007 | TID-01 | Overview & Building the ATCC System | 2025-02-27 | 2025-02-27 | Ruby Kushwah | Build | 3- Completed | 3 | Day 1: 3
US-008 | TID-01 | Training Of Various Vehicle Classification Models | 2025-02-28 | 2025-02-28 | Ruby Kushwah | Coding | 3- Completed | 6 | Day 2: 3; Day 3: 3
US-008 | TID-02 | Testing Of Various Vehicle Classification Models | 2025-03-01 | 2025-03-01 | Ruby Kushwah | Coding | 3- Completed | 4 | Day 4: 4
US-009 | TID-01 | Develop a deep learning-based vehicle classification models | 2025-03-03 | 2025-03-03 | Ruby Kushwah | Design | 3- Completed | 6 | Day 5: 4; Day 6: 2
US-010 | TID-01 | Creating A Live Tracker | 2025-03-04 | 2025-03-04 | Ruby Kushwah | Coding | 3- Completed | 3 | Day 8: 3
US-011 | TID-01 | Sorting Of the Detected Vehicles and its Number Plates, Frame IDs Into a Csv File For Better Classification | 2025-03-05 | 2025-03-05 | Ruby Kushwah | Design | 3- Completed | 6 | Day 9: 6
US-011 | TID-02 | Add Missing Values Like Frame IDs In the Csv File Through Data Processing | 2025-03-06 | 2025-03-06 | Ruby Kushwah | Coding | 3- Completed | 5 | Day 10: 5
US-012 | TID-01 | Visualize The Number Plates And Vechicles In The Traffic Video Using The Csv File | 2025-03-07 | 2025-03-07 | Ruby Kushwah | Coding | 3- Completed | 5 | Day 11: 3; Day 12: 2
SPRINT 4 BACKLOG
US-013 | TID-01 | Combining ANPR and ATCC systems into a cohesive platform | 2025-03-08 | 2025-03-08 | Ruby Kushwah | Integration Test | 3- Completed | 9 | Day 1: 3; Day 2: 2; Day 3: 3
US-013 | TID-02 | Optimizing for real-time performance | 2025-03-09 | 2025-03-09 | Ruby Kushwah | Design | 3- Completed | 6 | Day 4: 6
US-014 | TID-01 | Successful integration of ANPR and ATCC with optimized performance and real-time processing capabilities. | 2025-03-10 | 2025-03-10 | Ruby Kushwah | System Test | 3- Completed | 8 | Day 5: 4; Day 6: 4
US-015 | TID-01 | Implementing optimizations to improve model inference speed and accuracy. | 2025-03-11 | 2025-03-11 | Ruby Kushwah | Coding | 3- Completed | 8 | Day 8: 3; Day 9: 2; Day 11: 3
US-015 | TID-02 | Ensuring smooth data flow between ANPR and ATCC for dynamic decision-making | ####### | ######### | Ruby Kushwah | Integration Test | 3- Completed | 5 | Day 12: 5

## Sheet3
Sprint | Day | Impediments | Action Taken
s1 | 1 | Introduction to Computer Vision | Learning the basics of Computer Vision
s1 | 8 | Introduction to OCR | Learning about Optical Character Recognition
s2 | 16 | Introduction & Implementation Of ANPR | Implementing ANPR practically
s2 | 19 | Training Of Various YOLO Models | Training various YOLO models for vehicle and helmet detection
s2 | 23 | Processing Of Images | Reading & processing pre-trained images in various formats to extract text and detect number plates
s2 | 24 | Processing Of Video | Reading & processing pre-trained videos into frames & annotating them to detect vehicles and riders
s3 | 25 | Training and testing classification model | Training and testing various vehicle classification models like cars, trucks, buses, and motorcycles
s3 | 26 | Developing deep learning-based vehicle classification models | Developing a deep learning-based classification model for vehicle and helmet detection
s3 | 27 | Creating a Live Objects Tracker | Developing a live tracker for real-time vehicle, helmet, and triple riding detection using the system camera or webcam
s3 | 28 | Sorting & Adding Missing Value | Sorting detected vehicles, riders, and helmets with their frame IDs into a CSV file for further classification & processing missing values
s3 | 29 | Visualization | Visualizing number plates, detected helmets, and triple riding instances in traffic videos using CSV files
s4 | 30 | Frontend Development | Developed the entire frontend of the system with React.js for live monitoring and configuration
s4 | 31 | Backend Integration with Flask | Successfully integrated the frontend with backend APIs using Flask for seamless communication
s4 | 32 | Helmet Detection Implementation | Implemented helmet detection on riders using trained YOLO models to identify rule violations
s4 | 33 | Triple Riding Detection | Developed an algorithm using YOLO & image processing to detect triple riding cases from live video feeds
s4 | 34 | Performance optimization techniques | Implemented optimizations to improve model inference speed and accuracy for real-time processing
s4 | 36 | Classification | Classifying vehicles into categories such as cars, buses, motorcycles, and identifying helmet violations

## Sheet4
SL# | Sprint | Start Date | End Date | Assigned To | Task 1 | Task 2 | Task 3 | Task 4
1 | s1 | 2025-02-07 | 2025-02-18 | Ruby Kushwah | Introduction to Computer Vision | Introduction to OCR | Overview of the Topics | Clarifying Doubts with Mentor
2 | s2 | 2025-02-19 | 2025-02-25 | Ruby Kushwah | Overview & Implementing ANPR | Reading & Processing of Pre-Trained Images & Videos | YOLO Model Training | Extracting Text to Detect Number Plates Using Processed Images & Videos
3 | s3 | 2025-02-26 | 2025-03-04 | Ruby Kushwah | Developed a Deep Learning-based Vehicle Classification Model | Sorting & Adding Missing Values | Visualization | Detecting Vehicles, Their Number Plates & Helmet Violations from Videos
4 | s4 | 2025-03-05 | 2025-03-11 | Ruby Kushwah | System Integration and Real-Time Optimization | Frontend Development for Dashboard & Monitoring | Backend Integration Using Flask | Implementing Helmet & Triple Riding Detection for Traffic Monitoring